## Sheet1
This excel spreadsheet is an extract of the Ten-Year Network Development Plan (TYNDP) monitoring database of the Agency for the Cooperation of Energy Regulators. (Export date: 12.12.2018) It shows the evolution of the status and commissioning date of each investment in the scope of the Agency's Opinion on the implementation of the EU TYNDP 2016. The information in the spreadsheet is either extracted from the EU TYNDPs (2012, 2014, 2016) prepared by ENTSO-E or it was provided by the National Regulatory Authorities (NRAs) during the Agency's monitoring activities or consistency checks. The information provided by NRAs is based on the latest available information to the NRAs - i.e. typically based on the latest final/draft National Development Plan (NDP). Legal notice: The Agency for the Cooperation of Energy Regulators accept no responsibility or liability for any consequences arising from the use of the data contained in this document.
Investment name in EU TYNDP 2016 | Internal / interconnection | Substation 1 | Country / jurisdiction of Substation 1 | Substation 2 | Country / jurisdiction of Substation 2 | EU TYNDP cluster number | EU TYNDP investment number | Status and commissioning date in EU TYNDP 2012 | Status and commissioning date in 2014 ACER TYNDP monitoring | Status and commissioning date in EU TYNDP 2014 | Status and commissioning date in 2016 ACER TYNDP monitoring | Status and commissioning date in EU TYNDP 2016 (or - where different - in ACER Opinion No 08/2017) | Status and commissioning date in 2018 ACER TYNDP monitoring
Pedralva-Sobrado | Internal | Pedralva (PT) | PT | Sobrado (PT) | PT | 1 | 2 | planned (2017) | Planned (2020) | planned (2020) | Under construction (2022) | Permitting (2015) | Planned, but not yet in permitting (2022-2023)
Pedralva - Ponte de Lima | Internal | Pedralva (PT) | PT | Ponte de Lima (PT) | PT | 1 | 3 | design & permitting (2014/2015) | Design & permitting (2015) | design & permitting (2015) | Under construction (2015) | Under Construction (2016) | Commissioned (2017)
V.Minho -R.Pena-Fridão-Feira | Internal | V.Minho (by Ribeira de Pena) | PT | Feira (by Ribeira de Pena) | PT | 1 | 4 | design & permitting (2015/2016) | Design & permitting (2018) | design & permitting (2018) | Permitting (2021) | Permitting (2020) | Permitting (2022-2024)
Rib. Pena | Internal | Ribeira de Pena (PT) | PT | - | - | 1 | 474 | design & permitting (2015/2016) | Design & permitting (2017) | design & permitting (2017) | Permitting (2020) | Permitting (2020) | Permitting (2022-2024)
V.P.Aguiar-Carrap.-Estarreja | Internal | V. P. Aguiar (by Carrapatelo) | PT | Estarreja (by Carrapatelo) | PT | 1 | 476 | design & permitting (2013) | Design & permitting (2017) | design & permitting (2017) | Permitting (2020) | Permitting (2020) | Permitting (2022)
Fundão-Falagueira | Internal | Fundão (PT) | PT | Falagueira (PT) | PT | 2 | 9 | design & permitting (2015/2016) | Design & permitting | design & permitting (2017) | Under construction (2017) | Design (2017) | Planned, but not yet in permitting (2018)
Fundão | Internal | Fundão (PT) | PT | - | - | 2 | 484 | design & permitting (2015/2016) | Design & permitting (2017) | design & permitting (2017) | Under construction (2017) | Design (2017) | Planned, but not yet in permitting (2019)
Fridão | Internal | Fridão | PT | - | - | 1 | 941 |  |  | Planned (2017) | Planned, but not yet in permitting (2022) | Permitting (2022) | Permitting (2026-2030)
Aizkraukle(LV)-Panevėžys(LT) | Interconnection | Aizkraukle (LV) | LV | Panevežys (LT) | LT | 170 | 1065 |  |  | Under consideration (2030) | Under consideration (2030) | Under Consideration (2025) | Cancelled
Cornier - Chavalon 400 kV | Interconnection | CORNIER (FR) | FR | CHAVALON (CH) | CH | 199 | 1051 |  |  | Under consideration (2025) | Under consideration (after 2025) | Under Consideration (After 2030) | cancelled
Omagh South to South Donegal | Interconnection | South Donegal (IE) | IE | Omagh South (NI) | UK (NI) | 82 | 896 |  |  | Planned (2024) | Under consideration (2027) | N/A | Planned but not yet permitting (2029)
SE Fontefria 400/220kV | Internal | Fontefria (ES) | ES | - | - | 4 | 498 | design & permitting (2014) | Design & permitting (2016) | design & permitting (2016) | Permitting (2017) | Permitting (2017) | Permitting (2021)
Beariz 400kV (ES) | Internal | Beariz (ES) | ES | - | - | 4 | 499 | design & permitting (2014) | Design & permitting | design & permitting (2016) | Permitting (2017) | Permitting (2017) | Permitting (2021)
Beariz (ES) - Fontefria (ES) | Internal | Beariz (ES) | ES | Fontefria (ES) | ES | 4 | 18 | design & permitting (2014) | Design & permitting (2016) | design & permitting (2016) | Permitting (2017) | Permitting (2017) | Permitting (2021)
Fontefría (ES) - Vila Nova de Famalicão (PT) | Interconnection | Fontefría (ES) | ES | Vila Nova de Famalicão (PT) (By Ponte de Lima) | PT | 4 | 496 | design & permitting (2014) | design & permitting (2014) in ES; design & permitting (2016) in PT | design & permitting (2016) | Permitting (2017) in ES; Permitting (2018) in PT | Permitting (2018) | Permitting (2021)
Ponte de Lima (PT) | Internal | Ponte de Lima (PT) | PT | - | - | 4 | 500 | design & permitting (2014) | Design & permitting (2016) | design & permitting (2016) | Permitting (2018) | Permitting (2018) | Permitting (2021)
Rondissone (IT) -Trino (IT) | Internal | Rondissone (IT) | IT | Trino (IT) | IT | 21 | 922 |  |  | Planned (2019) | Permitting (2019) | Planning (2019) | Commissioned (2017)
Lacchiarella-Chignolo Po | Internal | Lacchiarella(IT) | IT | Chignolo Po(IT) | IT | 21 | 923 |  |  | Planned (2019) | Permitting (2019) | planning (2019) | Under construction (2019)
Vado-Vignole | Internal | Vado (IT) | IT | Vignole (IT) | IT | 21 | 1283 |  |  | Planned (2019) | Planned, but not yet in permitting (2019) | planning (2019) | Under construction (2019)
380 kV btw Milano and Brescia | Internal | Cassano (IT) | IT | Chiari (IT) | IT | 31 | 914 |  |  | Design & permitting (2022) | Planned, but not yet in permitting (2025) | Design & Permitting (2025) | Permitting (2022)
Rem. lim. in Central Italy | Internal | Villanova (IT) | IT | S. Barbara (IT) | IT | 33 | 1041 |  |  | Planned (2020) | Planned, but not yet in permitting (beyond 2023) | Planning (2025) | Planned, but not yet in permitting(long term)
Omagh South to Turleenan | Internal | Omagh South | UK (NI) | Turleenan | UK (NI) | 82 | 897 |  |  | Planned (2020) | N/A | N/A | Planned but not yet permitting (2029)
PST Vierraden | Internal | Vierraden | DE | - | - | 94 | 992 |  |  | Planned (2017) | N/A | Design & Permitting (2018) | Commissioned
New substation Reboria | Internal | Reboria (ES) | ES | - | - | 151 | 523 | design & permitting (2012-2014) |  | Under consideration (2026) | N/A (2026) | Planning (2020) | Under consideration (>2023)
Complementary connection | Internal | Offshore Hub OR Stevin - TBD | BE | Antwerp Area OR Izegem - TBD | BE | 120 | 933 |  |  | Under consideration (2030) | Under consideration (after the scope of NDP (2025 or later)) | Under Consideration (2025) | Under consideration (2026-2028)
1 GW to Antwerp area | Internal | Offshore Hub OR Stevin - TBD | BE | Doel (BE) - TBD | BE | 120 | 1053 |  |  | Under consideration (2030) | Under consideration (2025 or later) | Under Consideration (2025) | Under consideration (2026-2028)
2nd interco UK - BE | Interconnection | Kemsley (UK) for example - TBD | UK (GB) | Doel/Zandvliet (BE) for example - TBD | BE | 121 | 934 |  |  | Under consideration (2013) | Under consideration (2025) | Under Consideration (2025) | Under consideration (>2028)
New substation Sama | Internal | Sama (ES) | ES | - | - | 151 | 522 | design & permitting (2012-2014) | Planned | Under consideration (2026) | Planned, but not yet in permitting (2020) | Planning (2020) | Planned, but not yet in permitting (>2023)
Double circuit Gozon-Sama | Internal | GOZON (ES) | ES | SAMA (ES) | ES | 151 | 928 | design & permitting (N/A) | Design & permitting | Under consideration (2026) | Permitting (2020) | Planning (2020) | Under consideration (>2022)
New line 400 kV Castejón-Ichaso | Internal | Castejón | ES | Ichaso | ES | 255 | 1455 | design & permitting (2017) | Planned | N/A | Planned, but not yet in permitting (2020) | Planning (2020) | Permitting (2023)
Morella-La Plana | Internal | Morella (ES) | ES | La Plana(ES) | ES | 203 | 538 | design & permitting (2012-2015) | Design & permitting (2016) | Design & permitting (2018) | Permitting (2018) | Permitting (2018) | Permitting (2020)
La Plana/Morella-Godelleta | Internal | La Plana/Morella | ES | Godelleta | ES | 193 | 927 | design & permitting (2012-2015) | Planned | Under consideration (2023) | Planned, but not yet in permitting (2018) | Under Consideration (2023) | Under consideration (2025)
Back-to-back in Alytus | Internal | Alytus(LT) | LT | - | - | 123 | 1038 |  |  | Planned (2020) | Planned, but not yet in permitting (2025) | Planning (2020) | Cancelled
Escatrón-La Secuita | Internal | Escatron (ES) | ES | La Secuita (ES) | ES | 157 | 545 | design & permitting (2015) | Planned | Under consideration (2027) | Cancelled | Under Consideration (2027) | Under consideration (2027)
New substation Els Aubals | Internal | Els Aubals (ES) | ES | - | - | 157 | 546 | design & permitting (2015) | Planned | Under consideration (2027) | Cancelled | Under Consideration (2027) | Under consideration (2027)
New substation La Secuita | Internal | La Secuita (ES) | ES | - | - | 157 | 547 | design & permitting (2015) | Planned | Under consideration (2027) | Cancelled | Under Consideration (2027) | Under consideration (2027)
NOR-9-1 | Internal | NOR-9-1 | DE | area of Unterweser | DE | 129 | 943 |  |  | Under consideration (2028) | N/A | Under Consideration (2035) | Under consideration (N/A)
Great Belt II | Internal | Malling (DKW) | DK | Kyndby (DKE) | DK | 175 | 1000 |  |  | Under consideration (2030) | Under consideration (N/A) | Under Consideration (2030) | Under consideration (2030)
Cartuja-Arcos 400 kV | Internal | Cartuja | ES | Arcos | ES | 194 | 929 | design & permitting (2011/2014) | Design & permitting (2015) | Under consideration (2022) | Cancelled | Under Consideration (2029) | Permitting (2023)
New substation Cartuja | Internal | Cartuja (ES) | ES | - | - | 194 | 561 | design & permitting (2011/2014) | Design & permitting (2015) | Under consideration (2022) | Cancelled | Under Consideration (2029) | Permitting (2023)
Axis Caparacena-Baza-La Ribina | Internal | Caparacena (ES) | ES | La Ribina (ES) | ES | 13 | 31 | design & permitting (2016) | Planned | Under consideration (2025) | Cancelled | Under consideration (2025) | Permitting (2025)
New substation Baza | Internal | Baza (ES) | ES | - | - | 13 | 569 | design & permitting (2016) | Planned | Under consideration (2025) | Cancelled | Under consideration (2025) | Permitting (2025)
New substation La Ribina | Internal | La Ribina (ES) | ES | - | - | 13 | 570 | design & permitting (2016) | Planned | Under consideration (2025) | Planned, but not yet in permitting (N/A) | Under consideration (2025) | Permitting (2025)
further HCDC connections C | Internal | Schleswig-Hostein | DE | Baden-Würtemberg / Bavaria | DE | 133 | 956 |  |  | Under consideration (2030) | N/A | Under Consideration (After 2030) | Under consideration (N/A)
Merchant line "Castasegna (CH) - Mese (IT)" | Interconnection | Castasegna | CH | Mese | IT | 250 | 1384 | design & permitting (2018) | Planned | N/A | Permitting (N/A) | Design & permitting (2019) | Permitting(2021)
HVDC Gatica-Cubnezais | Interconnection | Gatica (ES) | ES | Cubnezais(FR) | FR | 16 | 38 | under consideration (ca. 2020) | under consideration (2020) | Planned (2023) | Under consideration (before 2023) | Planning (2025) | Permitting (2025)
PST Arkale | Internal | Arkale (ES) | ES | - | - | 184 | 594 | design & permitting (2016) |  | Planned (2019) | Under construction (2017) | Permitting (2017) | Commissioned (2017)
DC Güstrow - Area Isar | Internal | Güstrow (DE) | DE | Area of Isar (DE) | DE | 133 | 958 |  |  | Under consideration (2034) | Under consideration (N/A) | Under Consideration (After 2030) | Under consideration (N/A)
further HVDC connections A | Internal | Lower Saxony | DE | North Rhine-Westphalia | DE | 133 | 969 |  |  | Under consideration (2030) | Planned, but not yet in permitting (2025) | Under Consideration (After 2030) | Under consideration (N/A)
Southern Massif Central | Internal | La Gaudière (FR) | FR | Rueyres (FR) | FR | 158 | 597 | under consideration (long term) | Under consideration | under consideration (2023) | Under consideration (2023) | Planning (2025) | Permitting (2020)
further HVDC connections B | Internal | Lower Saxony | DE | Hesse/Baden-Würtemberg | DE | 133 | 970 |  | N/A | Under consideration (2030) | N/A | Under Consideration (After 2030) | Under consideration (N/A)
Savoie - Piémont | Interconnection | Grande Ile (FR) | FR | Piossasco (IT) | IT | 21 | 55 | design & permitting (2017/2018) | under construction (2019) | Under construction (2019) | Under construction (2019) | Under construction (2019) | Under construction (2019)
Vigy Uchtelfangen (or beyond) | Interconnection | Vigy (FR) | FR | Uchtelfangen (DE) | DE | 244 | 1245 |  |  | Under consideration (2030) | Under consideration (Beyond 2025) in FR; N/A in DE | Planning (2030) | Planned, but not yet in permitting (2030) in FR; Planned, but not yet in permitting (<2030) in DE
Geneva's lake (West) | Interconnection | Genissiat (FR) | FR | Verbois (CH) | CH | 22 | 57 | under consideration (long term) | under consideration | Planned (2020) | Planned, but not yet in permitting (2018) | Planning (2018) | Commissioned (2018)
France -Belgium | Interconnection | Avelin/Mastaing (FR) | FR | Horta (new 400-kV substation) (BE) | BE | 23 | 60 | under consideration (2018-2020) | under consideration (2018-2020) | Planned (2021) | Under consideration (2022) in FR; Permitting (2022) in BE | Design (2022) | Planned, but not yet in permitting (2021)
BRABO III: Liefkenshoek - Mercator | Internal | Liefkenshoek (BE) | BE | Mercator (BE) | BE | 297 | 604 | design & permitting (2017) | Design & permitting (Q4 2017) | design & permitting (2018) | Permitting (2023) | Design & Permitting (2023) | Under consideration (2025)
BRABO II: Zandvliet - Lillo - Liefkenshoek | Internal | Zandvliet | BE | Lillo - Liefkenshoek | BE | 297 | 445 | design & permitting (2017) | Design & permitting (Q4 2017) | design & permitting (2018) | Permitting (2020) | Design & Permitting (2020) | Under construction (2020)
BRABO II: Lillo 380 | Internal | Lillo (BE) | BE | - | - | 297 | 605 | design & permitting (2017) | Design & permitting (Q4 2017) | design & permitting (2018) | Permitting (2019) | Design & Permitting (2019) | Under construction (2019)
Van Eyck - Gramme (conditional upgrade / reinforcement to HTLS) | Internal | Van Eyck | BE | Gramme | BE | 252 | 1050 |  |  |  |  | Under Consideration (2025) | Under consideration (2029)
Horta-Mercator: HTLS upgrade | Internal | Horta (BE) | BE | Mercator (BE) | BE | 236 | 608 | design & permitting (2016-2020) | Design & permitting (2016-2020) | design & permitting (2019) | Permitting (2019) | Permitting (2019) | Under construction (2019)
BRABO I: PST 4 + Doel-Zandvliet | Internal | Zandvliet (BE) | BE | - | - | 24 | 609 | planned (2016-2020) | Planned (2016) | Under construction (2016) | Under construction (2016) | Under construction (2016) | Commissioned (2016)
IFA2 | Interconnection | Tourbe (FR) | FR | Chilling (GB) | UK (GB) | 25 | 62 | under consideration (2020) | under consideration (2020) | Design & permitting (2020) | Under consideration (2020) | Permitting (2020) | Under construction (2020)
216 | Internal | St. Peter (AT) | AT | Tauern (AT) | AT | 47 | 216 | design & permitting (2017/2019) | Design & permitting (2019) | design & permitting (2020) | Permitting (2020) | Permitting (2021) | Permitting (2023)
218 | Internal | Obersielach (AT) | AT | Lienz (AT) | AT | 26 | 218 | under consideration (long term) | Under consideration (>2023) | under consideration (2023) | Under consideration (2023) | Planning (2024) | Planned, but not yet in permitting (2028)
63 | Interconnection | Lienz (AT) | AT | Veneto region (IT) | IT | 26 | 63 | planned (long term) | Under consideration (>2023) | planned (2023) | Under consideration (2023) | Planning (after 2024) | Cancelled
Muhlbach Eichstetten | Interconnection | Muhlbach | DE | Eichstetten | DE | 228 | 1231 |  |  | Under consideration (2026) | N/A | Planning (2025) | Planned, but not yet in permitting (2025 in NDP 2017-2030)
N/A | Interconnection | Prati di Vizze (IT) | IT | Steinach (AT) | AT | N/A | N/A | N/A | Design & permitting (2017) | N/A | N/A | Permitting (2019) | Under construction (2019)
614 | Interconnection | Nauders (AT) | AT | Glorenza (IT) | IT | 26 | 614 | under consideration (long term) | under consideration (2022) | Design & permitting (2018) | Under consideration (2019) | Design (2020) | Permitting (2022/23) in AT; Permitting (2021) in IT
N/A | Interconnection | Udine Sud (IT) | IT | Okroglo (SI) | SI | N/A | N/A | N/A | Planned (2022) | planned (2021) | N/A | Under Consideration (Beyond 2025) | Cancelled in SI; Under consideration (2028 or beyond) in IT
N/A | Internal | Udine Ovest (IT) | IT | Redipuglia (IT) | IT | N/A | N/A | N/A | Under construction (2016) | Under construction (2016) | N/A | Permitting (2018) | Commissioned (2017)
223 | Interconnection | Cirkovce (SI) | SI | Heviz (HU) Zerjavenec (HR) | HU | 141 | 223 | N/A | Planned (>2018) in SI; Commissioned (N/A) in HR | Design & permitting (2016) | Permitting (2016-2018) in SI | Design & Permitting (2019) | Permitting (2021) in SI; HU part is already constructed, connection works are feasible once the SI part is constructed
225 | Internal | Divaca (SI) | SI | Cirkovce (SI) | SI | 141 | 225 | planned (long term) | Under construction (2025) | Design & permitting (2020) | Permitting (2025 / 2020) | Design & Permitting (2025) | Permitting (> 2026)
OHL 400 kV Banja Luka - Lika | Interconnection | Banja Luka (BA) | BA | Lika (HR) | HR | 136 | 227 | under consideration (2020) | under consideration (2020) | under consideration (2021) | Under consideration (2030) | Under Consideration (2030) | Under consideration (2030)
OHL 400 kV Lika - Brinje | Internal | Lika(HR) | HR | Brinje(HR) | HR | 136 | 617 | planned (2020) | Planned (2020) | planned (2020) | Under consideration (2027) | Under Consideration (2025) | Under consideration (2030)
OHL 400 kV Lika - Velebit | Internal | Lika(HR) | HR | Velebit(HR) | HR | 136 | 618 | planned (2020) | Planned (2020) | planned (2020) | Under consideration (2027) | Under Consideration (2025) | Under consideration (2030)
Substation 400/110 kV Lika | Internal | Lika (HR) | HR | - | - | 136 | 619 | planned (2017) | Planned (2020) | planned (2018) | Under consideration (2027) | Under Consideration (2027) | Under consideration (2029)
Substation 400/220 kV Brinje | Internal | Brinje (HR) | HR | - | - | 136 | 620 | planned (2020) | Planned (2020) | planned (2020) | Under consideration (2027) | Under Consideration (2025) | Under consideration (2029)
ITA-6 | Interconnection | Slovenia (SI) | SI | Salgareda (IT) | IT | 150 | 616 | under consideration (long term) | Planned (>2022) | under consideration (2022) | Under consideration (2022) | Design & Permitting (2022) | Under consideration (> 2026) in SI; Permitting (2025) in IT
70 | Interconnection | Villanova (IT) | IT | Lastva (ME) | ME | 28 | 70 | under construction (2015) | under construction (2017) | under construction (2017) | Under construction (2019) | under construction (2019) | Under construction (2019)
86 | Internal | Foggia (IT) | IT | Villanova(IT) | IT | 127 | 86 | design & permitting (2015) | Under construction (2019) | Design & permitting (2019) | Permitting (2023) | Design & Permitting (2023 for Foggia-Gissi part) | Permitting (2024)
330 kV OHL Tartu-Valmiera | Interconnection | Tartu | EE | Valmiera | LV | 170 | 1010 |  |  | Under consideration (2030) | Under consideration (2023) in LV; Planned, but not yet in permitting (N/A) in EE | Under Consideration (2023) | Permittin (2023) in LV; Planned, but not yet in permitting (2024) in EE
Valmiera -Tsirguliina 330 kV | Interconnection | Tsirguliina | EE | Valmiera | LV | 170 | 1011 | planned (2015) | N/A | Under consideration (2030) | Under consideration (2024) in LV; Commissioned (N/A) in EE | Under Consideration (2024) | Permittin (2024) in LV; Planned, but not yet in permitting (2024) in EE
330 kV OHL Tartu-Balti (L300) | Internal | Balti | EE | Tartu | EE | 170 | 1012 | design & permitting (2016) | N/A | Under consideration (2030) | Planned, but not yet in permitting (N/A) | Planning (2024) | Planned, but not yet in permitting (2023)
Eesti-Tsirguliina 330kV OHL | Internal | Eesti | EE | Tsirguliina | EE | 170 | 1013 | planned (>2016) | N/A | Under consideration (2030) | Planned, but not yet in permitting (2013) | Planning (2025) | Planned, but not yet in permitting (2025)
TEC1-TEC2 | Internal | TEC1 | LV | TEC2 | LV | 170 | 1063 | planned (>2016) | N/A | Under consideration (2030) | Under consideration (2030) | Under Consideration (2025) | Cancelled
OHL 400 kV Konjsko - Velebit | Internal | Konjsko(HR) | HR | Velebit(HR) | HR | 136 | 633 | planned (2020) | Planned (2020) | planned (2020) | Under consideration (2027) | Under Consideration (2025) | Under consideration (2030)
ITA-7 | Interconnection | Sicily Area (IT) | TN | North Africa node | IT | 29 | 635 | design & permitting (long term) | under consideration | Under consideration (2030) | Planned, but not yet in permitting (N/A) | Under consideration (2022 in EU TYNDP 2016 / no commissioning date in draft NDP 2016 in IT) | Under consideration (2025)
N/A | Internal | Partanna (IT) | IT | Ciminna (IT) | IT | N/A | N/A | N/A | Under consideration | N/A | N/A | Under Consideration (Beyond 2025) | Under consideration (2028 or beyond)
Viskali (LV) - Musa (LT) | Interconnection | Viskali (LV) | LV | Musa (LT) | LT | 170 | 1064 |  |  | Under consideration (2030) | Under consideration (2030) | Under consideration (2025) | Cancelled
DKW-GB link | Interconnection | Revsing (DKW) | DK | Bicker Fen (GB) | UK (GB) | 167 | 998 | under consideration (2020) | N/A | Under consideratiojn (2020) | Under consideration (2030) | Permitting (2022) | Permitting (2023)
ITA-4 | Interconnection | Airolo (CH) | CH | Pallanzeno(IT)-Baggio(IT) | IT | 31 | 642 | under consideration (long term) | Design & permitting (2022) | Design & permitting (2022) | Permitting (N/A) | Design & Permitting (2025) | Permitting (2025)
Magenta substation | Internal | Magenta (IT) | IT | - | - | 31 | 932 | N/A | Design & permitting (2020) | Design & permitting (2020) | Permitting (N/A) | Design & Permitting (2025) | Under construction (2022)
91 | Internal | Foggia (IT) | IT | Benevento II (IT) | IT | 127 | 91 | under construction (2013-2014) | Under construction (2014) | under construction (2014) | Under construction (N/A) | 2nd phase: under construction (2019); 1st phase: commissioned (2014) | Under construction (2019)
96 | Internal | Deliceto (IT) | IT | Bisaccia (IT) | IT | 127 | 96 | design & permitting (mid term) | Design & permitting (2017) | design & permitting (2017) | Permitting (N/A) | Design & Permitting (2022) | Under construction (2021)
Spaak NL | Internal | Krimpen aan de Ijssel | NL | Dodewaard | NL | 168 | 894 |  |  | Under consideration (2025) | N/A (2025) | Under Consideration (After 2030) | Under construction (2030)
ITA-3 | Internal | Laino (IT) | IT | Altomonte(IT) | IT | 127 | 645 | design & permitting (2012/mid term) | Design & permitting (2017) | design & permitting (2017) | Permitting (N/A) | Design & Permitting (2022) | Permitting (long term)
ElecLink | Interconnection | Sellindge (UK) | UK (GB) | Mandarins (FR) | FR | 172 | 1388 |  |  | Design & permitting (2016) | Permitting (2019) | Design & Permitting (2019) | Under construction (2020)
90 | Internal | Calenzano (IT) | IT | Colunga (IT) | IT | 33 | 90 | design & permitting (mid term) | Design & permitting (2018) | design & permitting (2018) | Permitting (N/A) | Design & Permitting (2023) | Permitting(2023)
SACOI3 | Internal | Codrongianos | IT | Suvereto | IT | 299 | 1458 | planned (long term) | Under consideration | N/A | Under consideration (N/A) | Under Consideration (2023) | Planned, but not yet in permitting (2023)
R Vitkov | Internal | Vitkov (CZ) | CZ | - | - | 200 | 306 | planned (2017/2018) | Design & permitting (2020) | Design & permitting (2020) | Permitting (2020) | Design & Permitting (2020) | Under construction (2020)
R Vernerov | Internal | Vernerov (CZ) | CZ | - | - | 200 | 307 | planned (2013/2016) | Design & permitting (2017) | Design & permitting (2017) | Permitting (2017) | Under Construction (2017) | Under construction (2017)
Vernerov-Vitkov | Internal | Vernerov (CZ) | CZ | Vitkov (CZ) | CZ | 200 | 308 | planned (long term) | Design & permitting (2019) | Design & permitting (2019) | Permitting (2023) | Design & Permitting (2023) | Permitting (2024)
Vitkov-Prestice | Internal | Vitkov (CZ) | CZ | Prestice(CZ) | CZ | 200 | 309 | under consideration (long term) | Design & permitting (2021) | Design & permitting (2021) | Permitting (2020) | Design & Permitting (2020) | Permitting (2021)
R Kocin | Internal | Kocin (CZ) | CZ | - | - | 35 | 311 | design & permitting (long term) | Design & permitting (2022) | design & permitting (2024) | Permitting (2020) | Design & Permitting (2024) | Permitting (2024)
R Mirovka | Internal | Mirovka (CZ) | CZ | - | - | 200 | 312 | planned (long term) | Design & permitting (2020) | Design & permitting (2020) | Permitting (2020) | Design & Permitting (2020) | Permitting (2025)
Kocin-Mirovka | Internal | Kocin (CZ) | CZ | Mirovka (CZ) | CZ | 35 | 313 | planned (long term) | Design & permitting (2020) | Design & permitting (2024) | Permitting (2024) | Design & Permitting (2024) | Permitting (2025)
Mirkovka-V413 | Internal | Mirovka (CZ) | CZ | V413 (CZ) | CZ | 200 | 314 | planned (long term) | Design & permitting (2017) | Design & permitting (2020) | Permitting (2017) | Design & Permitting (2018) | Under construction (2019)
Kocin-Prestice | Internal | Kocin (CZ) | CZ | Prestice (CZ) | CZ | 35 | 315 | planned (long term) | Design & permitting (2024) | Design & permitting (2028) | N/A | Design & Permitting (2028) | Permitting (2028)
Mirovka-Cebin | Internal | Mirovka (CZ) | CZ | Cebin (CZ) | CZ | 35 | 316 | under consideration (long term) | Design & permitting (2024) | Design & permitting (2028) | N/A | Design & Permitting (2029) | Planned, but not yet in permitting (beyond 2029)
141 | Interconnection | Ishøj / Bjæverskov (DK) | DK | Bentwisch/Güstrow (DE) | DE | 36 | 141 | Planned (long term) | Design & permitting (2018) | Design & permitting (2018) | Permitting (2018) | Under construction (2018) | Under construction (2018)
Norway - Germany HVDC | Interconnection | Tonstad (NO) | NO | Wilster (DE) | DE | 37 | 142 | design & permitting (2018/2021) | Design & permitting (2018) | design & permitting (2018) | Planned, but not yet in permitting (Contructions finished in 2019, commissioning 2020) | Under construction (2020) | Under construction (2020)
Western corridor | Internal | (Southern part of Norway) (NO) | NO | (Southern part of Norway)(NO) | NO | 37 | 406 | design & permitting (2016 (2013-2018)) | Design & permitting (2016) | design & permitting (2020) | Under construction (2021-2022) | Under construction (2020) | Under construction (2020)
Lonny-Achène-Gramme: HTLS upgrade (under study) | Interconnection | Lonny (FR) | FR | Gramme (BE) | BE | 280 | 1008 |  |  | Under consideration (2030) | Under consideration (Long term) | Under Consideration (2025) | Under consideration (2030)
Greenconnector | Interconnection | Verderio | IT | Sils i.D. | CH | 174 | 1014 |  |  | Design & permitting (2018) | N/A | Design & Permitting (2021) | Under construction (2022)
Audorf - Kassoe | Interconnection | Audorf (DE) | DE | Kassö (DK) | DK | 39 | 144 | under consideration (2017) | Under consideration (2019) in DK; Planned (2019) in DE | Planned (2019) | Permitting (2019) in DK; Planned, but not yet in permitting (N/A) in De | permitting (2020) | Permitting (2020) in DK; Under construction (2020) in DE
LUXEMBOURG RING | Internal | Heisdorf (LU) | LU | Berchem (LU) | LU | 40 | 447 | design & permitting (2012/2017) | (2016) | design & permitting (2017) | Under construction (2017) | Under construction (2017) | Commissioned (2016)
BELUX Long-Term | Interconnection | Bascharage (LU) | LU | Aubange (BE) | BE | 40 | 650 | under consideration (2020) | under consideration (2020) in BE; Under consideration (>2017) in LU | under consideration (2020) | Under consideration (2023) in BE; Under consideration (2022) in LU | Under consideration (2022) | Under consideration (2035) in BE; Under consideration (N/A) in LU
Dollern - Stade | Internal | Dollern (DE) | DE | Stade (DE) | DE | 164 | 149 | design & permitting (mid term) | (2015) | Planned (2022) | N/A | Permitting (2021) | Under construction (2020)
Conneforde-Wilhelmshaven | Internal | Conneforde (DE) | DE | Fedderwarden (DE) | DE | 208 | 150 | design & permitting (long term) | Planned (2018) | design & permitting (2018) | Permitting (2018) | Permitting (2020) | Under construction (2020)
Nordergründe | Internal | Offshore- Wind park Nordergründe (DE) | DE | Inhausen (DE) | DE | 42 | 160 | design & permitting (mid term) | (2016) | Under construction (2016) | N/A | Under construction (2016) | Commissioned
DolWin2 | Internal | Cluster DolWin2 (DE) | DE | Dörpen/West (DE) | DE | 42 | 654 | under construction (mid term) | (2015) | under construction (2015) | N/A | Under construction (2016) | Commissioned (2016)
DolWin3 | Internal | Cluster DolWin3 (DE) | DE | Dörpen/West (DE) | DE | 42 | 655 | design & permitting (mid term) | (2017) | Under construction (2017) | N/A | Under construction (2017) | Under construction (2018)
BorWin3 | Internal | Cluster BorWin3 | DE | Emden/Ost (DE) | DE | 191 | 656 | design & permitting (mid term) | (2018) | design & permitting (2018) | N/A | Under Construction (2019) | Under construction (2019)
BorWin4 | Internal | Cluster BorWin4 (DE) | DE | area of Cloppenburg/East | DE | 129 | 658 | under consideration (long term) | (2019) | Design & permitting (2019) | N/A | Under Consideration (2029) | Under consideration (N/A)
SylWin2 | Internal | Cluster SylWin2 (DE) | DE | Büttel (DE) | DE | 192 | 659 | under consideration (long term) |  | under consideration (2023) | N/A | Under Consideration (2025) | Under consideration (2028 in offshore NDP 2017-2030)
Wolmirstedt-Isar | Internal | Wolmistedt (DE) | DE | Isar (DE) | DE | 130 | 665 | under consideration (long term) | Planned (2022) | Planned (2022) | Planned, but not yet in permitting (2022) | Planning (2025) | Permitting (2025)
HVDC Line A South - Ultranet | Internal | Osterath (DE) | DE | Philippsburg (DE) | DE | 254 | 660 | under consideration (long term) | Planned (2019) | Design & permitting (2019) | Planned, but not yet in permitting (N/A) | Permitting (2021) | Permitting (2023)
HVDC Line C | Internal | Brunsbüttel, Wilster | DE | Großgartach, Grafenrheinfeld | DE | 235 | 664 | under consideration (long term) | Planned (2022) | Planned (2022) | Planned, but not yet in permitting (N/A) | Planning (2025) | Permitting (2025)
Conneforde - Emden | Internal | Conneforde | DE | Emden/Ost | DE | 207 | 939 | under consideration (long term) |  | Planned (2019) | Permitting (2019) | Permitting (2021) | Permitting (2021)
Brunsbüttel - Niebüll | Internal | Brunsbüttel (DE) | DE | Niebüll | DE | 258 | 667 | under consideration (long term) |  | Planned (2018) | Planned, but not yet in permitting (N/A) | Permitting (2019) | Permitting (2020)
HVDC Line A-North | Internal | Emden East (DE) | DE | Osterath (DE) | DE | 132 | 661 | under consideration (long term) | Planned (2022) | Planned (long term) | Planned, but not yet in permitting (N/A) | Planning (2025) | Permitting (2025)
HVDC Line B | Internal | Wehrendorf (DE) | DE | Urberach (DE) | DE | 133 | 662 | under consideration (long term) | Under consideration | under consideration (2022) | Under consideration (N/A) | Under Consideration (Afte 2030) | Under consideration (N/A)
Cloppenburg East - Merzen | Internal | Cloppenburg East (DE) | DE | Merzen (DE) | DE | 132 | 663 | under consideration (long term) | Planned (2022) | under consideration (2022) | Planned, but not yet in permitting (2022) | Planning (2022) | Permitting (2024)
Dollern - Hamburg/Nord | Internal | Dollern (DE) | DE | Hamburg/Nord (DE) | DE | 251 | 147 | design & permitting (mid term) | Design & permitting (2015) | Under construction (2017) | Permitting (N/A) | Under Construction (2018) | Under construction (2019)
Audorf - Hamburg/Nord | Internal | Audorf (DE) | DE | Hamburg/Nord (DE) | DE | 251 | 148 | design & permitting (mid term) | Design & permitting (2017) | design & permitting (2017) | Permitting (N/A) | Under Construction (2018) | Commissioned (2017)
Ganderkesee - Wehrendorf | Internal | Wehrendorf (DE) | DE | Ganderkesee (DE) | DE | 208 | 151 | design & permitting (mid term) | Design & permitting (2017) | design & permitting (2017) | Permitting (N/A) | Permitting (2021) | Under construction (2021)
Niederrhein-Dörpen | Internal | Niederrhein (DE) | DE | Dörpen/West (DE) | DE | 208 | 156 | design & permitting (mid term) | Design & permitting (2018) | design & permitting (2018) | Permitting (N/A) | Permitting (2019) | Permitting (2021)
Wahle - Mecklar | Internal | Wahle (DE) | DE | Mecklar (DE) | DE | 164 | 157 | design & permitting (mid term) | Design & permitting (2018) | design & permitting (2018) | Permitting (N/A) | Permitting (2021) | Under construction (2021)
Hansa PowerBridge | Interconnection | Station SE4 | SE | Güstrow (DE) | DE | 176 | 995 |  |  | Under consideration (2025) | Planned, but not yet in permitting (2025) | Planning (2025) | Planned, but not yet in permitting (2026 in NDP 2017-2030)
Rommerskirchen - Weißenthurm | Internal | Rommerskirchen (DE) | DE | Weißenthurm (DE) | DE | 135 | 179 | design & permitting (mid term) | Under construction (2017) | Under construction (2017) | Under construction (N/A) | Permitting (2018) | Under construction (2020)
Kontek 2 | Interconnection | Bjæverskov (DK2) | DK | Bentwisch (DE) | DE | 179 | 1016 |  |  | Under consideration (2030) | Under consideration (2019) in DK; N/A in DE | Under Consideration (2030) | Under consideration (2030) in DK; Under consideration (N/A) in DE
Kruckel - Dauersberg | Internal | Kruckel (DE) | DE | Dauersberg (DE) | DE | 135 | 188 | planned (long term) | Design & permitting (2020) | Design & permitting (2020) | Permitting (2021) | Permitting (2022) | Under construction (2023)
Unterweser - Conneforde | Internal | Conneforde (DE) | DE | Unterweser (DE) | DE | 207 | 675 | under consideration (long term) | Under consideration | under consideration (2024) | Under consideration (2024) | Under Consideration (2024) | Under consideration (This investment has not received an approval during the last NDP 2017-2030 process. The indicated commissioning date by TSOs is 2029.)
Dollern - Elsfleth/West | Internal | Dollern (DE) | DE | Elsfleht/West (DE) | DE | 207 | 676 | under consideration (long term) | Under consideration | under consideration (2024) | Planned, but not yet in permitting (2024) | Planning (2024) | Planned, but not yet in permitting (2029)
Dollern - Landesbergen | Internal | Dollern (DE) | DE | Landesbergen (DE) | DE | 164 | 677 | under consideration (long term) | Planned (2022) | Planned (2022) | Under consideration (N/A) | Planning (2023) | Permitting (2023)
Urberach - Daxlanden | Internal | Urberach (DE) | DE | Daxlanden (DE) | DE | 134 | 680 | under consideration (long term) | Planned (2022) | Planned (2021) | Planned, but not yet in permitting (2025) | Planning (2022) | Permitting (2023)
Großgartach - Endersbach | Internal | Großgartach (DE) | DE | Endersbach (DE) | DE | 206 | 682 | under consideration (long term) | Under consideration (2018) | Planned (2019) | Under consideration (2020) | Planning (2025) | Under consideration (N/A)
Herbertingen - Tiengen | Internal | Herbertingen (DE) | DE | Tiengen (DE) | DE | 198 | 984 | planned (long term) |  | Planned (2020) | Under consideration (N/A) | Planning (2020) | Under consideration (This investment was not approved within the last NDP 2017-2030. The commissioning date as indicated by TSOs within their draft NDP 2017-2030 is 2025.)
Daxlanden-Eichstetten | Internal | Daxlanden (DE) | DE | Eichstetten (DE) | DE | 134 | 176 | under consideration (2020) | Planned (2021) | under consideration (2020) | Planned, but not yet in permitting (2021) | Planning (2021) | Planned, but not yet in permitting (2021)
Südwestkuppelleitung | Internal | Vieselbach (DE) | DE | Redwitz (DE) | DE | 205 | 193 | design & permitting (mid term) | Under construction (2015) | design & permitting (2015) | Under construction (N/A) | Under Construction (2016) | Commissioned (2016)
Mecklar - Grafenrheinfeld | Internal | Mecklar (DE) | DE | Grafenrheinfeld (DE) | DE | 164 | 685 | under consideration (long term) | Planned (2022) | Planned (2020) | Planned, but not yet in permitting (2022) | Planning (2029) | Planned, but not yet in permitting (2027)
Altenfeld-Grafenrheinfeld | Internal | Schalkau / area of Altenfeld (DE) | DE | area of Grafenrheinfeld (DE) | DE | 204 | 686 | under consideration (long term) | Under consideration | Under consideration (long term) | Under consideration (N/A) | Planning (2024) | Planned, but not yet in permitting (2027 in NDP 2017-2030)
Redwitz - Schwandorf | Internal | Redwitz (DE) | DE | Schwandorf (DE) | DE | 206 | 687 | under consideration (long term) | Planned (2020) | Planned (2020) | Permitting (2020) | Permitting (2023) | Permitting (2023)
Altheim - Isar | Internal | Raitersaich (DE) | DE | Altheim (DE) | DE | 206 | 688 | under consideration (long term) | Under consideration | under consideration (2024) | Planned, but not yet in permitting (2024) | Planning (2026) | Planned, but not yet in permitting (2026)
Offshore Wind Baltic Sea (I) | Internal | OWF Cluster Baltic Sea East (DE) | DE | Lubmin (DE) | DE | 242 | 194 | design & permitting (2012-2020) |  | design & permitting (2031) | N/A | Under Construction (2018) | Under consideration (N/A)
212 Isar/Altheim/Ottenhofen - St. Peter | Interconnection | Isar (DE) | DE | St. Peter (AT) | AT | 47 | 212 | design & permitting (2017) | design & permitting (2018) in DE; N/A in AT | design & permitting (2018) | Permitting (N/A) in DE; Permitting (2019) in AT | Permitting (2020) | Permitting (2022) in DE; Under construction (2022) in AT
219 | Internal | Westtirol (AT) | AT | Zell-Ziller (AT) | AT | 47 | 219 | design & permitting (2013-2020) | Planned (2013-2018) | Planned (2021) | Under consideration (2021) | planning (2022) | Planned, but not yet in permitting (2024/25/26)
Greenlink | Interconnection | Great Island (to be confirmed) | IE | Pembroke (to be confirmed) | UK (GB) | 286 | 1385 |  |  | Planned (2018) | Planned, but not yet in permitting (after 2020) | Design (2022) | Permitting (2023) in UK; Planned, but not yet in permitting (2023) in IE
Vöhringen (DE) - Westtirol (AT) | Interconnection | Vöhringen / Leupolz (DE) | DE | Westtirol (AT) | AT | 47 | 689 | planned (long term) | Planned (2020) in DE; N/A in AT | Planned (2020) | Planned, but not yet in permitting (N/A) in DE; Under consideration (2019) in AT | Planning (2023) | Under consideration (2023) in DE; Planned, but not yet in permitting (2024/25) in AT
1. SK-HU interconnection | Interconnection | Gabcikovo (SK) | SK | Gonyü area (HU) | HU | 48 | 214 | under consideration (2016) | Planned (2018) | Planned (2018) | Planned, but not yet in permitting (2018) in SK; Permitting (2018) in HU | Planning (2020) | Permitting (2020) in SK; Planned, but not yet in permitting (2020) in HU
997 Pleinting - St. Peter | Interconnection | Pleinting (DE) | DE | St. Peter (AT) | AT | 187 | 997 |  |  | Under consideration (2022) | Permitting (2019) in AT; N/A in DE | Planning (2022) | Under construction (2022) in AT; Planned, but not yet in permitting (2024) in DE
2. SK-HU interconnection | Interconnection | Rimavská Sobota (SK) | SK | Sajóivánka (HU) | HU | 48 | 695 | under consideration (2016) | Planned (2018) | Planned (2018) | Planned, but not yet in permitting (2018) in SK; Permitting (2018) in HU | Planning (2020) | Permitting (2020) in SK; Planned, but not yet in permitting (2020) in HU
Hunew 1 | Internal | Sajóivánka (HU) | HU | - | - | 48 | 696 | under consideration (2016) | Planned (2016) | Planned (2018) | Planned, but not yet in permitting (2018) | planning (2019) | Planned, but not yet in permitting (2019)
Hunew 1 | Internal | Sajóivánka (HU) | HU | - | - | 48 | 697 | under consideration (2016) | Planned (2016) | Planned (2018) | Planned, but not yet in permitting (2018) | planning (2019) | Planned, but not yet in permitting (2019)
Irish Scottish Links on Energy Study (ISLES) | Internal | Argyll Hub | UK (GB) | - | - | 189 | 1389 | under construction (Serbian part commissioned, Macedonian part : 2013) | N/A | Under consideration (2030) | N/A (2020-2030) | Under consideration (After 2030) | Under consideration (>2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Coleraine Hub | UK (GB) | - | - | 189 | 1390 | under consideration (2020) | N/A | Under consideration (2030) | N/A | Under consideration (After 2030) | Under consideration (>2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | coolkeeragh hub | UK (GB) | - | - | 189 | 1391 |  |  | Under consideration (2030) | N/A | Under consideration (After 2030) | Under consideration (>2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Argyll hub | UK (GB) | Coleraine | UK (GB) | 189 | 1392 |  |  | Under consideration (2030) | N/A (2020-2030) | Under consideration (After 2030) | Under consideration (>2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Coolkeeragh | UK (GB) | Coolkeeraghhub | UK (GB) | 189 | 1393 |  |  | Under consideration (2030) | N/A | Under consideration (After 2030) | Under consideration (>2030)
New_400 kV OHL RO-RS | Interconnection | Resita (RO) | RO | Pancevo (RS) | RS | 144 | 238 | design & permitting (2015 (2019?)) | design & permitting (2015) | design & permitting (2017) | Under construction (2017) | Under Construction (2017) | Commissioned (2018)
400 kV OHL Portile de Fier-Resita | Internal | Portile de Fier (RO) | RO | Resita (RO) | RO | 144 | 269 | design & permitting (2016) | Design & permitting (2016) | design & permitting (2017) | Under construction (2018) | Under Construction (2018) | Under construction (2021)
400 kV Substation Resita | Internal | Resita (RO) | RO | Resita (RO) | RO | 144 | 701 | design & permitting (N/A) | Design & permitting (2017) | design & permitting (2012) | Permitting (2018) | Permitting (2018) | Under construction (2021)
Upgrade of the existing 220kV double circuit OHL Resita –Timisoara – Sacalaz – Arad to 400kV double circuit line | Internal | Resita (RO) | RO | Arad (RO) | RO | 144 | 270 | design & permitting (2022) | Design & permitting (2022) | design & permitting (2022) | Permitting (2023) | Permitting (2023) | Permitting (2027)
400 kV Substation Timisoara | Internal | Timisoara (RO) | RO | Timisoara (RO) | RO | 144 | 705 | design & permitting (2022) | Design & permitting (2022) | design & permitting (2022) | Planned, but not yet in permitting (2023) | Design (2023) | Permitting (2023)
Irish Scottish Links on Energy Study (ISLES) | Internal | Coleraine hub | UK (NI) | Coolkeeragh hub | UK (NI) | 189 | 1396 | planned (>2015) | N/A | Under consideration (2030) | N/A | Under consideration (After 2030) | Under consideration (After 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Hunterston | UK (GB) | Coleraine | UK (NI) | 189 | 1398 | planned (>2015) | N/A | Under consideration (2030) | N/A (2020-2030) | Under consideration (After 2030) | Under consideration (After 2030)
NorthConnect | Interconnection | Sima | NO | Peterhead | UK (GB) | 190 | 1382 | planned (>2015) | N/A | Design & permitting (2020) | Under consideration (2021) | Design (2022) | Permitting (2023) in UK; Permitting (2022) in NO
Cluster DolWin 5 (NOR 1-1) | Internal | Cluster DolWin 5 (NOR-1-1) | DE | Halbemond | DE | 191 | 952 | planned (2015) | N/A | Under consideration (2021) | N/A (2022) | Under Consideration (2024) | Permitting (2024)
244 | Internal | Filippi(GR) | GR | Lagadas (GR) | GR | 147 | 244 | under construction (2013) | Under construction (2016) | under construction (2016) | Under construction (2015) | Under Construction (2019) | Commissioned (2016 )
256 | Interconnection | Maritsa East 1 (BG) | BG | N.Santa (GR) | GR | 142 | 256 | design & permitting (long term) | under consideration (2020) | design & permitting (2021) | Permitting (2021) | Permitting (2023) | Permitting (Beginning of 2023)
257 | Internal | Maritsa East 1 (BG) | BG | Plovdiv (BG) | BG | 142 | 257 | design & permitting (2014) | Design & permitting (2018) | design & permitting (2016) | N/A | Design & Permitting (2020) | Permitting (2020)
258 | Internal | Maritsa East 1 (BG) | BG | Maritsa East 3 (BG) | BG | 142 | 258 | design & permitting (2014) | Design & permitting | design & permitting (2016) | Permitting (2017) | Design & Permitting (2017) | Permitting (2020)
262 | Internal | Maritsa East 1 (BG) | BG | Burgas (BG) | BG | 142 | 262 | design & permitting (2014) | Under consideration (2019) | design & permitting (2016) | Permitting (2021) | Design & Permitting (2021) | Permitting (2021)
400kV OHL Cernavoda-Stalpu | Internal | Cernavoda (RO) | RO | Stalpu (RO) | RO | 138 | 273 | planned (2017) | Planned (2019) | Design & permitting (2019) | Permitting (2020) | Permitting (2020) | Permitting (2021)
400 kV OHL Smardan-Gutinas | Internal | Smardan (RO) | RO | Gutinas (RO) | RO | 138 | 275 | planned (2020) | Design & permitting (2020) | Design & permitting (2020) | Permitting (2020) | Permitting (2020) | Permitting (2022)
220kV Stalpu substation upgrade to 400 kV | Internal | Stalpu (RO) | RO | Stalpu (RO) | RO | 138 | 715 | planned (2018) | Planned (2019) | planned (2019) | Planned, but not yet in permitting (2020) | Permitting (2020) | Permitting (2021)
3. SK-HU interconnection | Interconnection | Velké Kapušany (SK) | SK | tbd (HU) | HU | 54 | 720 | under consideration (2021) | under consideration (2021) | under consideration (2021) | Under consideration (2029) | Under consideration (2029) | Under consideration (2029)
Vyskov-Cechy Stred | Internal | Vyskov (CZ) | CZ | Cechy stred (CZ) | CZ | 55 | 302 | design & permitting (2015) | Design & permitting (2016) | design & permitting (2016) | Commissioned (2015) | Under construction (2016) | Commissioned (2016)
Babylon-Bezdecin | Internal | Babylon (CZ) | CZ | Bezdecin (CZ) | CZ | 55 | 303 | planned (2016) | Design & permitting (2018) | Design & permitting (2018) | Permitting (2019) | Design & Permitting (2018) | Permitting (2023)
Babylon-Vyskov | Internal | Babylon (CZ) | CZ | Vyskov (CZ) | CZ | 55 | 304 | planned (2018) | Design & permitting (2019) | Design & permitting (2021) | Permitting (2021) | Design & Permitting (2019) | Permitting (2024)
Cluster DolWin6 | Internal | Cluster DolWin 6 (NOR-3-3) | DE | Emden/East | DE | 191 | 953 |  |  | Under consideration (2021) | N/A | Under Consideration (2023) | Permitting (2023)
Cluster BorWin 5 (NOR-7-1) | Internal | Cluster BorWin 5 (NOR-7-1) | DE | area of Cloppenburg/East | DE | 192 | 954 |  |  | Under consideration (2022) | N/A (2023) | Under Consideration (2025) | Permitting (2025 based on the last Offshore-NDP)
Krajnik-Baczyna | Internal | Krajnik (PL) | PL | Baczyna (PL) | PL | 230 | 353 | planned (2020) | Planned (2020) | planned (2020) | Planned, but not yet in permitting (2021) | Planning (2021) | Under construction (2021)
Mikułowa - Świebodzice | Internal | Mikułowa (PL) | PL | Świebodzice (PL) | PL | 230 | 355 | planned (2020) | Planned (2020) | planned (2020) | Planned, but not yet in permitting (2022 ) | Planning (2022) | Planned, but not yet in permitting (2023)
Gubin | Internal | Gubin | PL | - | - | 229 | 1274 | planned (2020) | Planned (2020) | planned (2030) | Planned, but not yet in permitting (N/A) | Under Consideration (After 2030) | Under consideration (after 2030)
Ostrołęka-Stanisławów | Internal | Ostroleka (PL) | PL | Stanislawów (PL) | PL | 123 | 373 | design & permitting (2020) | Planned (2020) | design & permitting (2020) | Permitting (2021) | Design & Permitting (2021) | Under construction (2023)
Kozienice-Siedlce Ujrzanów | Internal | Kozienice (PL) | PL | Siedlce Ujrzanów (PL) | PL | 123 | 374 | design & permitting (2020) | Design & permitting (2019) | design & permitting (2020) | Permitting (2019) | Design & Permitting (2019) | Commissioned (2018)
330 kV Panevezys-Musa | Internal | Panevezys (LT) | LT | Musa (LT) | LT | 124 | 378 | planned (2018) | Planned (2022) | planned (2022) | Planned, but not yet in permitting (2023) | Planning (2023) | Under consideration (2025)
Grobina (LV) - Imanta (LV) | Internal | Grobina (LV) | LV | Imanta (LV) | LV | 124 | 385 | design & permitting (2018) |  | Under construction (2018) | Under construction (2019) | Under Construction (2019) | Under construction (30/12/2019)
Ekhyddan-Nybro-Hemsjö | Internal | Ekhyddan (SE) | SE | Nybro/Hemsjö (SE) | SE | 124 | 733 | under consideration (2019) | Planned (2023) | Planned (2021) | Permitting (2023) | Design & Permitting (2023) | Permitting (2023)
330 kV line VAE-Kruonis | Internal | Visaginas (LT) | LT | Kruonis (LT) | LT | 170 | 380 | planned (2020) | Planned (2022) | Under consideration (2022) | Planned, but not yet in permitting (2024) | Under Consideration (2024) | Cancelled
330 kV line Vilnius-Neris | Internal | Vilnius (LT) | LT | Neris (LT) | LT | 170 | 382 | planned (2020) | Planned (2022) | planned (2022) | Planned, but not yet in permitting (2024) | Planning (2024) | Planned, but not yet in permitting (2024)
3rd EE-LV | Internal | Kilingi-Nomme (EE) | EE | R-TEC2 (LV) | LV | 62 | 386 | planned (2020) | N/A | planned (2020) | Permitting (2020) | Design & Permitting (2020) | Permitting (2020)
Harku-Sindi 330kV OHL | Internal | Harku (EE) | EE | Sindi (EE) | EE | 62 | 735 | design & permitting (2018) | Design & permitting (2020) | design & permitting (2018) | Permitting (2020) | Design & Permitting (2020) | Permitting (2020)
Pyhänselkä-Petäjävesi | Internal | Pyhänselkä (FI) | FI | Petäjävesi (FI) | FI | 197 | 742 | design & permitting (2020) | Design & permitting (2021) | design & permitting (2023) | Permitting (2023) | Design & Permitting (2023) | Planned, but not yet in permitting (2023)
NOR-11-1 | Internal | NOR-11-1 | DE | area of Wilhelmshaven | DE | 129 | 946 |  | N/A | Under consideration (2026) | N/A | Under Consideration (2032) | Under consideration (N/A)
Bramford - Twinstead | Internal | Bramford (GB) | UK (GB) | Twinstead (GB) | UK (GB) | 69 | 747 | Design & Permitting (2018/2019) | Design & permitting | Design & Permitting (2022) | Permitting (2018) | Design & Permitting (2023) | Permitting(TBC)
NOR-12-1 | Internal | NOR-12-1 | DE | area of Wilhelmshafen | DE | 129 | 948 |  |  | Under consideration (2027) | N/A | Under Consideration (2034) | Under consideration (N/A)
NEMO | Interconnection | Richborough (GB) | UK (GB) | Zeebrugge (BE) | BE | 74 | 443 | planned (2018) | Planned (2018) | Design & permitting (2018) | Permitting (2018) | under construction (2019) | Under construction (2019)
Richborough - Canterbury | Internal | Richborough (GB) | UK (GB) | Canterbury (GB) | UK (GB) | 74 | 449 | planned (2019/2020) |  | planned (2018) | Permitting (N/A) | Design & Permitting (2018) | Under construction (2019)
SELL - DUNG Reconductoring | Internal | Sellindge (GB) | UK (GB) | Dungeness (GB) | UK (GB) | 74 | 450 | planned (2014/2015) | Planned | Design & permitting (2015) | Planned, but not yet in permitting (2017) | Under construction (2016) | Commissioned
STEVIN | Internal | Zomergem (BE) | BE | Zeebrugge (BE) | BE | 75 | 444 | design & permitting (2014) | Design & permitting (Q1 2016) | design & permitting (2018) | Under construction (2017) | Under construction (2017) | Commissioned (2017)
Modular Offshore Grid | Internal | Offshore platform(s) | BE | Stevin(Zeebrugge) | BE | 75 | 752 | planned (2016) | Design & permitting (Q4-2016 (phase1) Q4-2017 (phase2)) | Design & permitting (2018) | Permitting (2019) | Permitting (2019) | Under construction (2019)
Western HVDC Link | Internal | Hunterston (GB) | UK (GB) | Deeside (GB) | UK (GB) | 77 | 452 | design & permitting (2015/2016) | Under construction | design & permitting (2016) | Under construction (2016) | Under construction (2017) | Commissioned (2017)
Eastern HVDC Link | Internal | Peterhead (GB) | UK (GB) | Hawthorn Pit (GB) | UK (GB) | 298 | 453 | planned (2018/2019) | Design & permitting (2019) | Design & permitting (2020) | Permitting (2023) | Under Consideration (2023) | Planned, but not yet in permitting (2023+)
NOR-13-1 | Internal | NOR-13-1 | DE | Kreis Segeberg | DE | 129 | 950 |  |  | Under consideration (2025) | N/A | Under Consideration (2031) | Under consideration (N/A)
HINP-SEAB New Double Circuit | Internal | Hinkley Point (GB) | UK (GB) | Seabank (GB) | UK (GB) | 78 | 458 | design & permitting (2019/20) | Under consideration (2020) | design & permitting (2019) | Under consideration (2020) | Design & Permitting (2022) | Permitting (2024)
WYLF-PEMB HVDC Link | Internal | Wylfa (GB) | UK (GB) | Pembroke (GB) | UK (GB) | 79 | 769 | planned (2020/21) | Design & permitting (2022) | planned (2025) | Permitting (2022) | Under consideration (2024) | Under consideration (2025+)
462 | Interconnection | Woodland (IE) | IE | Turleenan (NI) | UK (NI) | 81 | 462 | design & permitting (2016) | design & permitting (2017) | design & permitting (2017) | Permitting (2019) | N/A | Permitting (2023) in UK; Permitting (2027) in IE
Srananagh - South Donegal | Internal | Srananagh (IE) | IE | New substation in South Donegal (IE) | IE | 82 | 463 | under consideration (2020) | Design & permitting (2020) | Planned (2020) | Permitting (2020) | N/A | Planned but not yet permitting (2027)
Extension of Ourique | Internal | Ourique (PT) | PT | - | - | 85 | 780 | planned (2018/2019) |  | planned (2025) | Planned, but not yet in permitting (2024) | Planning (2024) | Planned, but not yet in permitting (2023-2026)
F.Alentejo-Ourique-Tavira | Internal | F. Alentejo (by Ourique) | PT | Tavira (by Ourique) | PT | 85 | 779 | planned (2018/2019) |  | planned (2025) | Planned, but not yet in permitting (2024) | planning (2025) | Planned, but not yet in permitting (2023-2027)
East Coast Offshore | Internal | Under Consideration (GB) | UK (GB) | Under Consideration (GB) | UK (GB) | 86 | 781 | under consideration (long term) | Under consideration | under consideration (2023) | Under consideration (2022) | Under construction (2026) | Under consideration (2026+)
East Coast Offshore | Internal | Under Consideration (GB) | UK (GB) | Under Consideration (GB) | UK (GB) | 86 | 782 | under consideration (long term) |  | under consideration (2020) | Permitting (N/A) | Under construction (2026) | Under consideration (2026+)
BorWin6 (NOR-7-2) | Internal | Cluster BorWin6 (NOR-7-2) | DE | area of Wilhelmshafen | DE | 192 | 955 | design & permitting (2015) | N/A | Under consideration (2023) | N/A | Under Consideration (2030) | Under consideration (2030 in last Offshore-NDP)
Grafenrheinfeld - Großgartach | Internal | Grafenrheinfeld (DE) | DE | Großgartach (DE) | DE | 206 | 990 | planned (2017) | N/A | Planned (2019) | Planned, but not yet in permitting (2020) | Planning (2022) | Planned, but not yet in permitting (2022)
Wurmlach (AT) - Somplago (IT) Interconnection | Interconnection | SOMPLAGO | IT | WURMLACH | AT | 210 | 1380 | design & permitting (2012) | N/A | Design & permitting (2017) | N/A | Permitting (2018) | Permitting (2021) in IT; N/A in AT
Interco Iceland-UK | Interconnection | tbd | IC | tbd | UK (GB) | 214 | 1082 | under consideration (2020) | N/A | Under consideration (2030) | N/A (2027) | Under Consideration (2030) | Planned, but not yet in permitting (2030)
EuroAsia Interconnector | Internal | Korakia (Crete)Site | GR | Athens Site | GR | 219 | 1410 | design & permitting (2015) | N/A | Planned (2020) | N/A | N/A (2022) | Permitting (2022)
EuroAsia Interconnector | Interconnection | Vasilikos Site | CY | Korakia (Crete)Site | GR | 219 | 1409 | design & permitting (2015) | N/A | Planned (2022) | Under consideration (2022) in CY; N/A in GR | Planning (2022) | Permitting (2020) in CY; Permitting (2022) in GR
EuroAsia Interconnector | Interconnection | Hadera Site | IL | Vasilikos Site | CY | 219 | 1407 | design & permitting (2017) | N/A | Planned (2018) | Under consideration (2018) | Planning (2019) | N/A
Southern Aegean Interconnector | Internal | Kandeliousa | GR | Syrna | GR | 293 | 1435 | planned (2019) | N/A | Design & permitting (2020) | N/A | Design (2021) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2025 in draft EU TYNDP 2018)
Southern Aegean Interconnector | Internal | Levitha | GR | Syrna | GR | 293 | 1433 | design & permitting (2015) | N/A | Design & permitting (2020) | N/A | Design (2020) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2025 in draft EU TYNDP 2018)
Southern Aegean Interconnector | Internal | KINAROS | GR | LEVITHA | GR | 293 | 1434 | design & permitting (2015) | N/A | Design & permitting (2020) | N/A | Design (2021) | Under consideration(The project is not included in the latest NDP in GR. The expected commissioning date is 2024 in draft EU TYNDP 2018)
Southern Aegean Interconnector | Internal | LEVITHA | GR | KORAKIACRETE | GR | 293 | 1432 | under consideration (2019) | N/A | Design & permitting (2020) | N/A | Design (2021) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2025 in draft EU TYNDP 2026)
Southern Aegean Interconnector | Internal | LAVRIO | GR | LEVITHA | GR | 293 | 1431 | under consideration (2020) | N/A | Design & permitting (2020) | N/A | Design & Permitting (2020) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2024 in draft EU TYNDP 2018)
2nd interconnecter between Belgium and Germany | Interconnection | to be defined (BE) | BE | to be defined (DE) | DE | 225 | 1107 | design & permitting (2016) | N/A | Under consideration (2030) | Under consideration (after the scope fo NDP (2025 or later) in BE; N/A in DE | Planning (2025) | Under consideration (> 2028) in BE; Under consideration (2025) in DE
ALEGrO | Interconnection | Area of Oberzier -Aachen/Düren(DE) | DE | Area of Lixhe - Liege(BE) | BE | 92 | 146 | design & permitting (2017) | Planned (2018) in DE; Design & Permitting (Q4 2018) in BE | design & permitting (2019) | Permitting (N/A) in DE; Permitting (2020) in BE | Permitting (2020) | Under construction (2020)
Reinforcements SE2-3 in Sweden | Internal | Sweden bidding area SE2 | SE | Sweden bidding area SE3 | SE | 126 | 403 | under consideration (2015) | Planned (2019) | N/A | Under consideration (2025) | Under Consideration (2025) | Under consideration (2025)
Krajnik-Vierraden | Interconnection | Vierraden (DE) | DE | Krajnik (PL) | PL | 94 | 139 | design & permitting (long term) | N/A | design & permitting (2017) | Permitting (2020) | Under construction (2018) | Commissioned (2018)
Krajnik | Internal | Krajnik (PL) | PL | - | - | 94 | 796 | design & permitting (2014) | Design & permitting (2017) | design & permitting (2017) | Under construction (2020) | Design & Permitting (2020) | Under construction (2019)
400 kV OHL Varna-Burgas | Internal | Varna(BG) | BG | Burgas(B+A1210:H1210G) | BG | 138 | 800 | planned (2016) | Under consideration (2020) | planned (2018) | Permitting (2022) | Planning (2024) | Permitting (2021)
FI5 KI-PS | Internal | Keminmaa (FI) | FI | Pyhänselkä (FI) | FI | 96 | 801 | under consideration (2019) | Under consideration (2021) | under consideration (2024) | Under consideration (2024) | planning (2024) | Planned, but not yet in permitting (2024)
Ostrołęka-Olsztyn Mątki | Internal | Ostroleka (PL) | PL | Olsztyn Matki (PL) | PL | 123 | 335 | design & permitting (2017) | Design & permitting (2017) | design & permitting (2017) | Under construction (2018) | Design & Permitting (2018) | Commissioned (2018)
Doetinchem-Niederrhein | Interconnection | Niederrhein (DE) | DE | Doetinchem (NL) | NL | 113 | 145 | design & permitting (>=2013) | Design & Permitting (2016) | design & permitting (2016) | Permitting (2018) in NL; Permitting (N/A) in DE | Under Construction (2017) | Under construction (2019/09) in NL; Under construction (2018) in DE
Noord-West 380 kV | Internal | Eemshaven (NL) | NL | Diemen (NL) | NL | 103 | 438 | design & permitting (2018) | (2019) | design & permitting (2018) | N/A (2019) | Design & Permitting (2020) | Under construction (2020)
Zuid-West 380 kV | Internal | Borssele (NL) | NL | Tilburg (NL) | NL | 103 | 439 | design & permitting (2016) | (2020) | design & permitting (2016) | N/A (2021) | Design & Permitting (2025) | Under construction (2022/Q4)
Randstad380 | Internal | Maasvlakte (NL) | NL | Beverwijk (NL) | NL | 103 | 440 | under construction (2016) |  | under construction (2017) | N/A (2018) | Under construction (2019) | Under construction (2018/Q4)
Upgrade Dutch Ring | Internal | Zwolle (NL) | NL | Maasbracht (NL) | NL | 103 | 441 | under consideration (long term) | (2021) | under consideration (2019) | Under consideration (2019) | planning (2030) | Planned, but not yet in permitting (2030)
France Ireland Interconnector | Interconnection | West Wexford or East Cork (IE) | IE | La Martyre (FR) | FR | 107 | 810 | under consideration (long term) | under consideration (long term) | under consideration (2025) | Under consideration (2025) | Under Consideration (2026) | Under consideration (2026) in FR; Planned, but not yet in permitting (2026) in IE
Norway - Great Britain | Interconnection | Kvilldal (NO) | NO | Blythe (GB) | UK (GB) | 110 | 424 | design & permitting (2018/2021) | Under consideration (2020) | design & permitting (2018) | Under consideration (N/A) | Under Construction (2021) | Under construction (2021)
3rd AC Finland-Sweden north | Interconnection | Finland North (FI) | FI | Sweden bidding area SE1/SE2 | SE | 111 | 396 | under consideration (2021) | under consideration (2025) in SE; under consideration (>2021) in FI | under consideration (2025) | Under consideration (2025-2028) in SE; under consideration (2025) in FI | Under Consideration (2025) | Planned, but not yet in permitting (2025) in SE; Under consideration (2025) in FI
DKE-PL-1 | Interconnection | Avedøre (DK) | DK | Dunowo (PL) | PL | 234 | 1236 | N/A | N/A | N/A | Under consideration (N/A) | Under Consideration (after 2030) | Under consideration (after 2030)
LEG1 | Interconnection | SALOUM (EG), TOBRUK (LIBYA) | EG - LY | MIRES (GR Crete) | GR | 284 | 1405 | N/A | N/A | N/A | N/A | Under consideration (2019) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2021 in draft EU TYNDP 2018)
TuNur | Interconnection | Rejim Maatoug 400kV | TN | Montalto 400kV | IT | 283 | 1378 | N/A | N/A | N/A | N/A | Permitting (2020) | Under consideration (2022)
Kontiskan 2 - Renewal | Interconnection | Lindome (SE3) | SE | Vester Hassing (DkV) | DK | 238 | 1240 | N/A | N/A | N/A | Under consideration (N/A) in DK / Cancelled (N/A) in SE | Under Consideration (After 2030) | Under consideration (After 2030) in DK; Under consideration (N/A) in SE
Upgrade Meeden - Diele | Interconnection | Meeden [NL] | NL | Diele [DE] | DE | 245 | 1246 | N/A | N/A | N/A | N/A (2020) | Planning (2019) | Under construction (2020/Q1)
Endrup - Idomlund | Internal | Idomlund (DK) | DK | Endrup (DK | DK | 167 | 436 | N/A | N/A | Planned (2020) | Under consideration (2022) | Planning (2022) | Permitting (2022)
Baczyna | Internal | Baczyna | PL | - | - | 230 | 1035 | N/A | N/A | Planned (2018) | Planned, but not yet in permitting (2022) | Permitting (2021) | Under construction (2022)
ALEGrO - AC reinforcements in Belgium | Internal | Lixhe | BE | Herderen | BE | 92 | 1045 | N/A | N/A | Design & permitting (2017) | Under construction (2017) | Under construction (2017) | Under construction (2019)
886 | Internal | Seyring | AT | Neusiedl/Zaya | AT | 186 | 886 | N/A | N/A | Planned (2021) | Planned, but not yet in permitting (2021) | Design (2021) | Permitting (2022/23)
Volpago substation | Internal | Volpago (IT) | IT | - | - | 26 | 1039 | N/A | N/A | Planned (2020) | Planned, but not yet in permitting (2020) | planning (2025) | Planned, but not yet in permitting (2025)
DE-AT-CH connection | Interconnection | Border area (DE-AT) | DE-AT | Rüthi (CH) | CH | 198 | 136 | N/A | N/A | Planned (2022) | N/A (>2020) | Under Consideration (2023) | Under consideration (N/A)
Emden - Halbemond | Internal | Emden/Ost | DE | Halbemond | DE | 207 | 940 | N/A | N/A | Planned (2021) | N/A | Planning (2022) | Planned, but not yet in permitting (2025)
Conneforde - Cloppenburg East | Internal | Conneforde (DE) | DE | Cloppenburg (DE) | DE | 132 | 666 | N/A | N/A | Planned (2022) | Planned, but not yet in permitting (2022) | Planning (2022) | Permitting (2024)
Rommelsb. - Herbertingen | Internal | Rommelsbach (DE) | DE | Herbertingen (DE) | DE | 198 | 985 | N/A | N/A | Planned (2018) | N/A | Permitting (2020) | Under construction (2020)
Wullenstetten - border area (DE-AT) | Interconnection | Wullenstetten (DE) | DE | Austrian National border (AT) | AT | 198 | 986 | N/A | N/A | Planned (2022) | Planned, but not yet in permitting (N/A) | Planning (2020) | Under consideration (N/A)
Kreis Segeberg - Siems | Internal | Kreis Segeberg | DE | Göhl | DE | 209 | 935 | N/A | N/A | Under consideration (2021) | Permitting (2021) | Planning (2022) | Planned, but not yet in permitting (2022)
WestCoast Line, North v2 | Interconnection | Niebüll (DE) | DE | Endrup (DKW) | DK | 183 | 1018 | N/A | N/A | Planned (2022) | Planned, but not yet in permitting (2022) | Planning (2022) | Planned, but not yet in permitting (2021) in DE; Permitting (2022) in DK
PST Hradec | Internal | Hradec | CZ | - | - | 177 | 889 | N/A | N/A | Design & permitting (2016) | Under construction (2016) | Under Construction (2016) | Commissioned (2017)
Güstrow - Wolmirstedt | Internal | Güstrow (DE) | DE | Wolmirstedt (DE) | DE | 240 | 200 | N/A | N/A | N/A | N/A | Permitting (2020) | Permitting (2023)
New 400 kV interconnection line | Interconnection | New planned 400 kV Marijampole substation or exicting 400 kV Aytus substation. | LT | State border | LT | 170 | 1034 | N/A | N/A | Under consideration (2023) | Under consideration (2025) | Under Consideration (2031) | Planned, but not yet in permitting (2031)
DolWin 4 (NOR-3-2) | Internal | Cluster DolWin 4 (NOR 3-2) | DE | area of Cloppenburg | DE | 192 | 211 | N/A | N/A | Under consideration (2021) | N/A | Under Consideration (2028) | Under consideration (2028 in last Offshore-NDP)
Mezquita-Morella | Internal | Mezquita | ES | Morella | ES | 203 | 1069 | N/A | N/A | Design & permitting (2017) | Under construction (2016) | Permitting (2017) | Commissioned (2016)
Southern Aegean Interconnector | Internal | Kandeliousa | GR | Pergousa | GR | 293 | 1436 | N/A | N/A | Design & permitting (2020) | N/A | Design (2021) | Under consideration (The project is not included in the latest NDP in GR. The expected commissioning date is 2021 in draft EU TYNDP 2025)
Massenhoven - Van Eyck | Internal | Massenhoven (BE) | BE | Van Eyck (BE) | BE | 252 | 1456 | N/A | N/A | Planned (2020) | Under consideration (2020-2025) | Under Consideration (2025) | Under consideration (2024)
North Massif Central | Internal | Marmagne or Eguzon | FR | Rueyres | FR | 216 | 999 | N/A | N/A | Under consideration (2030) | Under consideration (2030) | Under Consideration (2030) | Under consideration (N/A)
Foretaille - Verbois | Internal | Foretaille (CH) | CH | Verbois (CH) | CH | 22 | 1291 | N/A | N/A | N/A | N/A | Design & Permitting (2023) | N/A
SS 400/110 kV Lastva | Internal | Lastva (ME) | ME | - | - | 28 | 624 | N/A | N/A | N/A | N/A | Under Construction (2016) | N/A
RigaCHP2-RigaHPP | Internal | RigaCHP2 | LV | RigaHPP | LV | 62 | 1062 | N/A | N/A | N/A | N/A | Under Consideration (2020) | Permitting (30.12.2020)
Upgrade Krimpen - Maasbracht | Internal | Krimpen aan de IJssel (NL) | NL | Maasbracht (NL) | NL | 103 | 442 | N/A | N/A | N/A | N/A | Design (2027) | 2027
B2B at Narva | Internal | Eesti | EE | - | - | 170 | 1117 | N/A | N/A | N/A | N/A | Planning (2024) | Planned, but not yet in permitting (2024)
SVC and control upgrades | Internal | Eesti 330 kV | EE | - | - | 170 | 1118 | N/A | N/A | N/A | N/A | Planning (2024) | Under consideration (2024)
Aubange-Moulaine: PSTs (under study) | Interconnection | Aubange (BE) | BE | Moulaine (FR) | FR | 173 | 1281 | N/A | N/A | N/A | N/A | Under Consideration (2020) | Planned, but not yet in permitting (2021) in BE; Planned, but not yet in permitting (2021) in FR
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | - | - | 189 | 1395 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub UK | UK (GB) | Trawsfynydd | UK (GB) | 189 | 1397 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | Trawsfynydd | UK (GB) | 189 | 1399 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Trawsfynydd | UK (GB) | - | - | 189 | 1400 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | Pembroke | UK (GB) | 189 | 1401 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | Pembroke | UK (GB) | 189 | 1402 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | Lodgewood | UK (GB) | 189 | 1403 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Southern Hub | UK (GB) | Lodgewood | UK (GB) | 189 | 1404 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Pembroke | UK (GB) | - | - | 189 | 1406 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Lodgewood | UK (GB) | - | - | 189 | 1408 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Southern Hub | UK (GB) | 189 | 1411 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | - | - | 189 | 1412 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Dunstown | UK (GB) | 189 | 1413 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Dunstown | UK (GB) | 189 | 1414 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Trawsfynydd | UK (GB) | 189 | 1415 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Trawsfynydd | UK (GB) | 189 | 1416 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Trawsfynydd | UK (GB) | - | - | 189 | 1417 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Dunstown | UK (GB) | - | - | 189 | 1418 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Woodland | UK (GB) | 189 | 1419 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Central Hub | UK (GB) | Woodland | UK (GB) | 189 | 1420 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Central Hub | UK (GB) | 189 | 1421 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | - | - | 189 | 1422 | N/A | N/A | N/A | N/A | N/A (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Louth | UK (GB) | 189 | 1423 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Louth | UK (GB) | 189 | 1424 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Louth | UK (GB) | 189 | 1425 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Louth | UK (GB) | - | - | 189 | 1426 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Woodland | UK (GB) | - | - | 189 | 1427 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Louth | UK (GB) | 189 | 1428 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Irish Scottish Links on Energy Study (ISLES) | Internal | Northern Hub | UK (GB) | Louth | UK (GB) | 189 | 1429 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Baczyna-Zielona Góra | Internal | Baczyna-Plewiska Indentation | PL | Zielona Góra | PL | 229 | 1270 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Zielona Góra - Plewiska | Internal | Zielona Góra | PL | Plewiska | PL | 229 | 1271 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Zielona Góra | Internal | Zielona Góra | PL | - | - | 229 | 1272 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Zielona Góra-Gubin | Internal | Zielona Góra | PL | Gubin | PL | 229 | 1273 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Gubin | Internal | Gubin | PL | - | - | 229 | 1274 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Gubin - Eisenhuettenstadt | Interconnection | Gubin | PL | Eisenhuettenstadt | DE | 229 | 1275 | N/A | N/A | N/A | N/A | Under consideration (After 2030) | Under consideration (after 2030)
Baczyna-Plewiska | Internal | Baczyna | PL | Plewiska | PL | 230 | 1232 | N/A | N/A | N/A | N/A | Planning (2022) | Under construction (2024)
380 kV Grid Reinforcement Beznau - Tiengen | Interconnection | Beznau (CH) | CH | Tiengen (DE) | DE | 231 | 1282 | N/A | N/A | N/A | N/A | Planning (2030) | Under consideration (2025 in NDP 2017-2030)
Additional measures | Interconnection | - | CH | - | DE | 231 | 1457 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (N/A)
Investments to be created | Interconnection | - | DK | - | DE | 232 | 1234 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030) in DK; Under consideration (N/A) in DE
Investments to be created | Interconnection | - | DK | - | NL | 237 | 1239 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030)
Fenno-Skan 1 renewal | Interconnection | Dannebo (SE3) | SE | Rauma (FI) | FI | 239 | 1241 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (2030) in FI; under consideration (N/A) in DE
AC Upgrade Bentwisch-Güstrow | Internal | Bentwisch (DE) | DE | Güstrow (DE) | DE | 240 | 1242 | N/A | N/A | N/A | N/A | Under Consideration (2025) | Planned, but not yet in permitting (2025 in NDP 2017-2030)
Upgrading of existing 220 kV line between SS Đakovo (HR) and SS Tuzla (BA) to 400 kV line | Interconnection | Đakovo | HR | Tuzla | BA | 241 | 1276 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030)
Upgrading of existing 220 kV line between SS Đakovo (HR) and Gradačac (BA) to 400 kV line | Interconnection | Đakovo | HR | Gradačac | BA | 241 | 1277 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030)
Upgrading existing 220 kV SS Đakovo to 400 kV | Internal | Đakovo | HR | - | - | 241 | 1278 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2028)
New double 400 kV line between SS Đakovo and location Razbojište | Internal | Đakovo | HR | Razbojište | HR | 241 | 1279 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (N/A)
New 400 kV overhead line Sombor (RS) – Ernestinovo (HR) | Interconnection | Ernestinovo | HR | Sombor | RS | 243 | 1269 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030)
AQUIND Interconnector | Interconnection | Lovedean (UK) | UK (GB) | Le Havre (FR) | FR | 247 | 1381 | N/A | N/A | N/A | N/A | Planning (2020) | Permitting (2022-2023) in FR; Permitting (2023) in UK(GB)
Offshore Wind Baltic (II) | Internal | - | DE | - | DE | 248 | 1248 | N/A | N/A | N/A | N/A | Under Consideration (2026) | Under consideration (N/A)
Cubnezais - Marmagne | Internal | Cubnezais | FR | Marmagne | FR | 249 | 1219 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (N/A)
Marmagne - Tabarderie | Internal | Marmagne | FR | Tabarderie | FR | 249 | 1221 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (N/A)
Uprate of Creys-St Vulbas | Internal | Creys(FR) | FR | Saint Vulbas (FR) | FR | 253 | 1224 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (2031)
PST in Cornier | Internal | Cornier (FR) | FR | - | - | 253 | 1225 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (2031)
New line 400 kV Muruarte-Ichaso | Internal | Muruarte | ES | Ichaso | ES | 255 | 1251 | N/A | N/A | N/A | N/A | Planning (2020) | Permitting (2023)
Long-term inter-connector DE-NL | Interconnection | to be defined (DE) | DE | to be defined (NL) | NL | 256 | 1252 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (2030) in NL; Under consideration (N/A) in DE
HU-RO | Interconnection | Jozsa | HU | Oradea | RO | 259 | 1205 | N/A | N/A | N/A | N/A | Under Consideration (After 2030) | Under consideration (2030)
Interconnector GB-NL | Interconnection | - | UK (GB) | - | NL | 260 | 1255 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030)
Belgium-Netherlands: further evolution | Interconnection | Van Eyck (BE) OR Zandvliet (BE) - TBC | BE | Maasbracht (NL) OR Kreekrak (NL) - TBC | NL | 262 | 1257 | N/A | N/A | N/A | N/A | Under Consideration (2022) | Under consideration (2030) in BE; Under consideration (2022) in NL
Rüthi - Bonaduz/Grynau | Internal | Rüthi | CH | Grynau & Bonaduz | CH | 263 | 1258 | N/A | N/A | N/A | N/A | Under Consideration (2023) | N/A
Beznau - Mettlen | Internal | Beznau | CH | Mettlen | CH | 264 | 1259 | N/A | N/A | N/A | N/A | Design & Permitting (2025) | N/A
Pradella - La Punt | Internal | Pradella | CH | La Punt | CH | 264 | 1284 | N/A | N/A | N/A | N/A | Design & Permitting (2020) | N/A
Bassecourt - Mühleberg | Internal | Bassecourt | CH | Mühleberg | CH | 264 | 1287 | N/A | N/A | N/A | N/A | Design & Permitting (2025) | N/A
Mettlen - Ulrichen | Internal | Mettlen | CH | Ulrichen | CH | 264 | 1288 | N/A | N/A | N/A | N/A | Design & Permitting (2025) | N/A
Grimsel connection | Internal | Innertkirchen | CH | Ulrichen | CH | 265 | 1260 | N/A | N/A | N/A | N/A | Planning (2029) | N/A
Lago Bianco connection | Internal | - | CH | - | CH | 265 | 1289 | N/A | N/A | N/A | N/A | Planning (2029) | N/A
Magadino - Ulrichen | Internal | - | CH | - | CH | 265 | 1290 | N/A | N/A | N/A | N/A | Planning (2029) | N/A
Bickigen - Chippis - Chamoson | Internal | Bickigen | CH | Chamoson | CH | 266 | 1261 | N/A | N/A | N/A | N/A | Design & Permitting (2019) | N/A
Chippis - Lavorgo | Internal | Chippis | CH | Lavorgo | CH | 266 | 1286 | N/A | N/A | N/A | N/A | Design & Permitting (2024) | N/A
Magadino | Internal | - | CH | - | CH | 266 | 1285 | N/A | N/A | N/A | N/A | Design & Permitting (2019) | N/A
Hansa Power Bridge 2 | Interconnection | Substation SE4 | SE | Güstrow (DE) | DE | 267 | 1262 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (N/A) in SE; Under consideration (2035) in DE
Portile de Fier (RO) - Djerdap (RS) 2nd | Interconnection | Portile de Fier | RO | Djerdap | RS | 268 | 1263 | N/A | N/A | N/A | N/A | Under Consideration (2035) | Under consideration (2030)
Uprate D.Rodrigo-Aljarafe | Internal | D.Rodrigo | ES | Aljarafe | ES | 269 | 1228 | N/A | N/A | N/A | N/A | Planning (2017) | Commissioned (2018)
Uprate Aljarafe-Santiponce | Internal | Aljarafe | ES | Santiponce | ES | N/A | 1229 | N/A | N/A | N/A | N/A | Planning (2019) | Permitting (2019)
Aragón region -Marsillón | Interconnection | Aragón region | ES | Marsillon | FR | 270 | 1211 | N/A | N/A | N/A | N/A | Planning (2025) | Under consideration (2027) in FR; Planned, but not yet in permitting (2027) in ES
New axis Ejea-Aragón region 400 kV | Internal | Ejea de los Caballeros | ES | Aragón region | ES | 270 | 1212 | N/A | N/A | N/A | N/A | Planning (2025) | Planned, but not yet in permitting (2027)
Ejea de los Caballeros subestation | Internal | Ejea de los Caballeros | ES | - | - | 270 | 1214 | N/A | N/A | N/A | N/A | Planning (2025) | Planned, but not yet in permitting (2027)
Aragón region subestation | Internal | Aragón region | ES | - | - | 270 | 1215 | N/A | N/A | N/A | N/A | Planning (2025) | Planned, but not yet in permitting (2027)
new 400-kV France-Switzerland interconnection | Interconnection | - | FR | - | CH | 274 | 1226 | N/A | N/A | N/A | N/A | Under Consideration (2030) | cancelled
New HVDC cross-border link between France and Switzerland | Interconnection | - | FR | - | CH | 275 | 1227 | N/A | N/A | N/A | N/A | Under Consideration (2030) | cancelled
HVDC Pamplona area -Cantegrit | Interconnection | Pamplona area | ES | Cantegrit | FR | 276 | 1206 | N/A | N/A | N/A | N/A | Planning (2025) | Under consideration (2027) in FR; Planned, but not yet in permitting (2027) in ES
Upgrade Cantegrit-Saucats | Internal | Cantegrit | FR | Saucats | FR | 276 | 1207 | N/A | N/A | N/A | N/A | Planning (2025) | Under consideration (2027)
Upgrade Cantegrit-Marsillon | Internal | Cantegrit | FR | Marsillon | FR | 276 | 1208 | N/A | N/A | N/A | N/A | Planning (2025) | Under consideration (2027)
Sofia West (BG) - Nis 2 (RS) 2nd | Interconnection | Sofia West (BG) | BG | Nis 2 (RS) | RS | 277 | 1266 | N/A | N/A | N/A | N/A | Under Consideration (2034) | Under consideration (2034)
Investments to be created | Interconnection | - | ES | - | FR | 278 | 1267 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (>2027) in ES; Under consideration (N/A) in FR
Maritsa East 1 (BG)- Nea Santa (GR) 2nd line | Interconnection | Maritsa East 1 (BG) | BG | Nea Santa (GR) | GR | 279 | 1452 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (2030) in BG; Under consideration (N/A) in GR
TuNur | Interconnection | Rejim Maatoug 400kV | TN | Montalto 400kV | IT | 283 | 1430 | N/A | N/A | N/A | N/A | Permitting (2020) | Under consideration (2025)
GridLink | Interconnection | Kemsley (Sittingbourne, UK) | UK (GB) | Warande (Gravelines, France) | FR | 285 | 1383 | N/A | N/A | N/A | N/A | Planning (2021) | Permitting (2022)
Greenwire South | Interconnection | Greenwire South Hub | IE | Pembroke (to be confirmed) | UK (GB) | 287 | 1439 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025+) in UK; Under consideration (2025) in IE
Greenwire South | Interconnection | Greenwire South Hub | IE | Dunstown, Laois or other tbc | UK (GB) | 287 | 1441 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025+) in UK; Under consideration (2025) in IE
Greenwire South | Internal | Greenwire South Hub | IE | Greenwire South substation AC1 | IE | 287 | 1442 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire South | Internal | Greenwire South Hub | IE | Greenwire South substation AC2 | IE | 287 | 1443 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire South | Internal | Greenwire South Hub | IE | Greenwire South substation AC3 | IE | 287 | 1444 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire South | Internal | Greenwire South Hub | IE | Greenwire South substation AC4 | IE | 287 | 1445 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire South | Internal | Greenwire South Hub | IE | Greenwire South substation AC5 | IE | 287 | 1446 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
MAREX UK-Ireland Intrconnector | Interconnection | Connah's Quay | UK (GB) | Finglas Dublin | IE | 289 | 1386 | N/A | N/A | N/A | N/A | Under consideration (2020) | Under consideration (2025+) in UK; Planned, but not yet in permitting (2025) in IE
MAREX UK-Ireland Intrconnector | Internal | Finglas Dublin | IE | Bellacorick Mayo | IE | 289 | 1387 | N/A | N/A | N/A | N/A | Under consideration (2020) | Planned, but not yet in permitting (2025)
Greenwire North | Interconnection | Greenwire North Hub | IE | Pentir (to be confirmed) | UK (GB) | 290 | 1440 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025+) in UK; Under consideration (2025) in IE
Greenwire North | Internal | Greenwire North Hub | IE | Woodlands or new Midlands 400/220V substation tba | IE | 290 | 1447 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire North | Internal | Greenwire North Hub | IE | Woodlands or new Midlands 400/220V substations tba | IE | 290 | 1369 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire North | Internal | Greenwire North Hub | IE | Greenwire North substation AC2 | IE | 290 | 1448 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire North | Internal | Greenwire North Hub | IE | Greenwire North substation AC3 | IE | 290 | 1449 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire North | Internal | Greenwire North Hub | IE | Greenwire North substation AC4 | IE | 290 | 1450 | N/A | N/A | N/A | N/A | Planning (2023) | Under consideration (2025)
Greenwire Loop Cable | Internal | Greenwire North Hub | IE | Grenwire South Hub | IE | 291 | 1454 | N/A | N/A | N/A | N/A | Under consideration (2022) | Under consideration (2025)
interconnection | Interconnection | Dublin Area ( to be agreed) | IE | Pentir (to be agreed) | UK (GB) | 292 | 1453 | N/A | N/A | N/A | N/A | Under consideration (2023) | Under consideration (2023+) in UK; Under conisderation (2025) in IE
Maali | Interconnection | Kergord Shetland tba | UK (GB) | tba near Bergen-Mongstad or Karsto- Blafalli | NO | 294 | 1356 | N/A | N/A | N/A | N/A | Under consideration (2023) | under consideration (2023) in NO; Planned, but not yet in permitting (>2025) in UK (GB)
Gallant | Internal | Glenluce | UK (GB) | Kilroot | UK (NI) | 295 | 1438 | N/A | N/A | N/A | N/A | Under consideration (2023) | Under consideration (2023) in NI Under consideration (2024+) in UK
N/A | Internal | Avise (IT) | IT | Chatillon (IT) | IT | N/A | N/A | N/A | N/A | N/A | N/A | Under Consideration (beyond 2025) | Under consideration (2028 or beyond)
N/A | Interconnection | Nosovice (CZ) | CZ | Varin (SK) | SK | N/A | N/A | N/A | N/A | N/A | N/A | Planned, but not yet in permitting (2026) | Planned, but not yet in permitting (2019) in CZ; Permitting (2026) in SK
N/A | Interconnection | Suceava (RO) | RO | Balti (MD) | MD | N/A | N/A | N/A | N/A | N/A | N/A | N/A (2023) | Permitting (2028)
COBRA Cable | Interconnection | Endrup (DK) | DK | Eemshaven (NL) | NL | 71 | 427 | N/A | N/A | N/A | N/A | Under Construction (2019) | Under construction (2019/Q3)
70 | Interconnection | Villanova (IT) | IT | Lastva (ME) | ME | 28 | 70 | under construction (2015) | under construction (2017) | under construction (2017) | Under construction (2019) | under construction (2019) | Under consideration (2026)
France-Alderney-Britain | Interconnection | Menuel (FR) | FR | Exeter (GB) | UK (GB) | 153 | 987 | N/A | Underc consideration (2022) | Planned (2020) | Permitting (2022) | Design & Permitting (2022) | Permitting (2022) in FR; Permitting (2022/23) in UK
Conceptual project | Internal | - | ES | - | - | 233 | 1235 | N/A | N/A | N/A | N/A | Under Consideration (2025) | Under consideration (2025)
Reinforcement in the Douro river area | Interconnection | - | ES | - | PT | 257 | 1253 | N/A | N/A | N/A | N/A | Under Consideration (2030) | Under consideration (>2030) in ES; Under consideration (N/A) in PT
ANAI: Abengoa Northern Atlantic Interconnection | Interconnection | Soto de Ribera | ES - FR - UK (GB) | Exeter | ES - FR - UK (GB) | 281 | 1379 | N/A | N/A | N/A | N/A | Under Consideration (2026) | Under consideration (2026) in ES; Under consideration (N/A) in FR; Under consideration (2026+) in UK
Britib | Interconnection | Gatica/Hernani, Cordemais and Langage/Indian Queens | ES - FR - UK (GB) | Gatica/Hernani, Cordemais and Langage/Indian Queens | ES - FR - UK (GB) | 296 | 1437 | N/A | N/A | N/A | N/A | Under Consideration (2021/2022) | Under consideration (N/A) in ES; Under consideration (2024) in FR; Under consideration (2025+) in UK
New substation Pamplona area | Internal | Pamplona area | ES | - | - | 276 | 1210 | N/A | N/A | N/A | N/A | Planning (2025) | Planned, but not yet in permitting (2027)
400 kV OHL Gadalin - Suceava | Internal | Gadalin (RO) | RO | Suceava (RO) | RO | 138 | 276 | N/A | N/A | N/A | N/A | Permitting (2023) | Permitting (2027)